## Sheet1
 | time axis 2017-10-23 to 2017-12-03
Game States & Start Screen | [6 empty] | Player & Enemy Classes | [5 empty] | Documentation | Advanced Levels/Level Class Adjustments and additions | [26 empty] | Documentation Overview
[6 empty] | ¦ |  |  | Collision Detection |  |  |  | Overview | Create our own personalized designs of the player and enemies | [10 empty] | (Possibly) Endless wave mode? Another game mode may be added. | [14 empty] | Pause and End Screen
[6 empty] | ¦------------------> | Projectile Class | [6 empty] | Advanced Enemies | [6 empty] | Advanced Projectiles | [9 empty] | Power Ups for Player |  |  |  |  | Options Menu and Sound Effects
This Gantt chart assumes the final day to work on Project 4 is Dec. 3rd
Anything task placed before another on the same line is a prerequisite to the task after it
Any tasks in the same color are corequisites/can be started at the same time
Lines and arrows may be placed to show a task as a prerequisite